## Sheet1
Date: | Activity: | Problems:
2016-11-16 | Create designs.
2016-11-18 | Present Designs to Tiff. | Tiff wanted a different set up.
2016-11-20 | Adjust color and design to her liking.
2016-11-21 | Perfect the template design.
2016-12-01 | Ben/Makayla - home page; Chris/Alex - products page; Shannon- photoshop promotional photos.
2016-12-02 | Ben/Makayla - home page/java research; Chris/Alex - products page; Shannon- photoshop promotional photos. | Products page: Table issues --> layout overhaul.
2016-12-05 | Ben/Makayla - java research/footer; Chris/Alex - fixing products page; Shannon - collect photos and create promo. | Footer: Alignment not cooperating --> Use specific align.
2016-12-07 | Ben/Makayla - finish home page/ footer; Chris/Alex - receive some photos from Tiff/fixing Products.
2016-12-09 | Ben/Makayla -finish footer; Chris/Alex - start inner product pages; Shannon - Coordinate overall design between pages.
2016-12-13 | Ben/Makayla/Chris/Alex/Shannon - coordinating product inner pages and perfecting tables.
2016-01-11 | Ben/Makayla - creation of the quote page; Chris/Shannon/Alex - contact page creation.
2016-01-12 | Ben/Makayla - creation of the quote page; Chris/Shannon/Alex - contact page fixing/emailing Tiff. | Quote: option buttons wont subtract --> use different buttons.
2016-01-13 | Ben/Makayla -Gallery java research; Chris/Alex - Revisiting products page.
2016-01-15 | Ben/Makayla -Gallery application.
2016-01-23 | Ben/Makayla - Complete the gallery. Chris/Alex - Rerevisit products page.
2016-02-15 | Ben/Makayla -quote; Shannon - edit journal.
2016-02-16 | Ben/Makayla -quote.
2016-02-20 | Ben/Makayla -quote.
2016-02-21 | Ben/Makayla -quote. Shannon - updates journal.
2016-02-22 | Ben/Makayla -quote.
2016-03-03 | Ben/Makayla -quote; Chris/Alex - finish up revisiting the homepage/ overall layout. | Overall layout: needed to be more dynamic and fluid --> expansion.
2016-03-05 | Ben/Makayla -quote; Chris/Alex - finish up revisiting the homepage/ overall layout.
2016-03-06 | Ben/Makayla -quote; Chris/Alex - finish up revisiting the homepage/ overall layout.
2016-03-08 | Ben/Makayla -quote;Chris/Shannon - Showcase Papers.
2016-03-10 | Ben/Makayla -quote; Chris/Shannon - Showcase Papers. | Showcase: Cancelling our appearance.
2016-04-11 | Ben/Makayla - conintue quote.
2016-04-12 | Ben/Makayla - GIVE UP ON QUOTE - quote. | Quote: impossible --> Gladeau assistance (even though I found the problem)
2016-04-14 | Ben/Makayla - GET HELP FOR QUOTE - quote.
2016-04-15 | Ben/Makayla - FINISH - quote.